## DataSheet
REQUEST_ID | JOB_NAME | EXTERNAL_ID | SECONDARY_EXTERNAL_ID | REQUEST_NAME | REQUEST_NAME_SUFFIX | SLA | ETA | AREA | MSO | LOB | SOFTWARE | CURRENT_ASSIGNED_TO | COMPANY | MODULE | STATUS | PROJECT_TYPE | PRIORITY | OU | MASTER PROJECT NAME | CLUSTER | PREV_PROJECT_COMPANY | PREV_PROJECT_EMPLOYEE | PREV_MODULE_COMPANY | PREV_MODULE_EMPLOYEE | PROXIMITY_GROUP_ID | HUB | NODE_NAME | DOCK STATUS | STREET NAME | APT | CITY | STATE | ZIPCODE | RECEIVED_DATE | FLAGGED | COMMENTS | CUSTOMER_DAYS | DESIGN_DAYS | REJECT_TYPE | REJECT_REASON | GROUP_POINTS | ASSIGN_DATE | P_QC | ESCALATED | ESCALATION_ASSIGNEE | NODEFLAG | NODE_FLAG_USER | NODE_FLAG_REASON | ADD_NEW_NODE | REJECT_DATE | CREATE_DATE | REJECT_SURVEY_DATE | REJECT_SURVEY_REMOVE_DATE | TOTAL_SURVEY_REJECTED_TIMES | DESIGN_COMPLETE_DATE | QC_ASSIGNED_DATE | QC_REJECTED_DATE | QC_RESUBMISSION_DATE | REJECTED_ORGANIZATION | TOTAL_PROJECT_AGE_IN_DAYS | TOTAL_DESIGN_ROLLOVER | TOTAL_QC_ROLLOVER | TOTAL_REJECTED_TO_SURVEY_DAYS | TOTAL_DAYS_IN_DESIGN | TOTAL DESIGN TIME IN DAYS | CONSTRUCTION SUB TYPE | 2ND QC_ASSIGNED_TO | 2ND QC_COMPANY | 2ND QC_TIME_IN_HOURS | 2ND QC_COMPLETED_DATE | 2ND QC_FOOTAGE | 2ND QC_POINTS | COAX_ASSIGNED_TO | COAX_COMPANY | COAX_TIME_IN_HOURS | COAX_COMPLETED_DATE | COAX_FOOTAGE | COAX_POINTS | DETERMINE PERMITS_ASSIGNED_TO | DETERMINE PERMITS_COMPANY | DETERMINE PERMITS_TIME_IN_HOURS | DETERMINE PERMITS_COMPLETED_DATE | DETERMINE PERMITS_FOOTAGE | DETERMINE PERMITS_POINTS | DRT QC_ASSIGNED_TO | DRT QC_COMPANY | DRT QC_TIME_IN_HOURS | DRT QC_COMPLETED_DATE | DRT QC_FOOTAGE | DRT QC_POINTS | FIBER_ASSIGNED_TO | FIBER_COMPANY | FIBER_TIME_IN_HOURS | FIBER_COMPLETED_DATE | FIBER_FOOTAGE | FIBER_POINTS | GIS-SPATIAL_ASSIGNED_TO | GIS-SPATIAL_COMPANY | GIS-SPATIAL_TIME_IN_HOURS | GIS-SPATIAL_COMPLETED_DATE | GIS-SPATIAL_FOOTAGE | GIS-SPATIAL_POINTS | JURISDICTION MONTORING_ASSIGNED_TO | JURISDICTION MONTORING_COMPANY | JURISDICTION MONTORING_TIME_IN_HOURS | JURISDICTION MONTORING_COMPLETED_DATE | JURISDICTION MONTORING_FOOTAGE | JURISDICTION MONTORING_POINTS | JURISDICTION SUBMITTAL_ASSIGNED_TO | JURISDICTION SUBMITTAL_COMPANY | JURISDICTION SUBMITTAL_TIME_IN_HOURS | JURISDICTION SUBMITTAL_COMPLETED_DATE | JURISDICTION SUBMITTAL_FOOTAGE | JURISDICTION SUBMITTAL_POINTS | MERGE QC_ASSIGNED_TO | MERGE QC_COMPANY | MERGE QC_TIME_IN_HOURS | MERGE QC_COMPLETED_DATE | MERGE QC_FOOTAGE | MERGE QC_POINTS | PACKAGE PREP_ASSIGNED_TO | PACKAGE PREP_COMPANY | PACKAGE PREP_TIME_IN_HOURS | PACKAGE PREP_COMPLETED_DATE | PACKAGE PREP_FOOTAGE | PACKAGE PREP_POINTS | PE STAMP_ASSIGNED_TO | PE STAMP_COMPANY | PE STAMP_TIME_IN_HOURS | PE STAMP_COMPLETED_DATE | PE STAMP_FOOTAGE | PE STAMP_POINTS | PENDING SUBMISSION_ASSIGNED_TO | PENDING SUBMISSION_COMPANY | PENDING SUBMISSION_TIME_IN_HOURS | PENDING SUBMISSION_COMPLETED_DATE | PENDING SUBMISSION_FOOTAGE | PENDING SUBMISSION_POINTS | PERMIT_ASSIGNED_TO | PERMIT_COMPANY | PERMIT_TIME_IN_HOURS | PERMIT_COMPLETED_DATE | PERMIT_FOOTAGE | PERMIT_POINTS | PERMIT ASSIGNMENT_ASSIGNED_TO | PERMIT ASSIGNMENT_COMPANY | PERMIT ASSIGNMENT_TIME_IN_HOURS | PERMIT ASSIGNMENT_COMPLETED_DATE | PERMIT ASSIGNMENT_FOOTAGE | PERMIT ASSIGNMENT_POINTS | PERMIT INVOICING_ASSIGNED_TO | PERMIT INVOICING_COMPANY | PERMIT INVOICING_TIME_IN_HOURS | PERMIT INVOICING_COMPLETED_DATE | PERMIT INVOICING_FOOTAGE | PERMIT INVOICING_POINTS | PREFIELD_ASSIGNED_TO | PREFIELD_COMPANY | PREFIELD_TIME_IN_HOURS | PREFIELD_COMPLETED_DATE | PREFIELD_FOOTAGE | PREFIELD_POINTS | PRISM SUBMITTAL_ASSIGNED_TO | PRISM SUBMITTAL_COMPANY | PRISM SUBMITTAL_TIME_IN_HOURS | PRISM SUBMITTAL_COMPLETED_DATE | PRISM SUBMITTAL_FOOTAGE | PRISM SUBMITTAL_POINTS | PRISM UPDATED SUBMITTAL_ASSIGNED_TO | PRISM UPDATED SUBMITTAL_COMPANY | PRISM UPDATED SUBMITTAL_TIME_IN_HOURS | PRISM UPDATED SUBMITTAL_COMPLETED_DATE | PRISM UPDATED SUBMITTAL_FOOTAGE | PRISM UPDATED SUBMITTAL_POINTS | QC_ASSIGNED_TO | QC_COMPANY | QC_TIME_IN_HOURS | QC_COMPLETED_DATE | QC_FOOTAGE | QC_POINTS | RDOF PACKAGE PREP_ASSIGNED_TO | RDOF PACKAGE PREP_COMPANY | RDOF PACKAGE PREP_TIME_IN_HOURS | RDOF PACKAGE PREP_COMPLETED_DATE | RDOF PACKAGE PREP_FOOTAGE | RDOF PACKAGE PREP_POINTS | RDOF PERMITS_ASSIGNED_TO | RDOF PERMITS_COMPANY | RDOF PERMITS_TIME_IN_HOURS | RDOF PERMITS_COMPLETED_DATE | RDOF PERMITS_FOOTAGE | RDOF PERMITS_POINTS | RDOF QC_ASSIGNED_TO | RDOF QC_COMPANY | RDOF QC_TIME_IN_HOURS | RDOF QC_COMPLETED_DATE | RDOF QC_FOOTAGE | RDOF QC_POINTS | RDOF WALKOUT_ASSIGNED_TO | RDOF WALKOUT_COMPANY | RDOF WALKOUT_TIME_IN_HOURS | RDOF WALKOUT_COMPLETED_DATE | RDOF WALKOUT_FOOTAGE | RDOF WALKOUT_POINTS | RDOF WALKOUT QC_ASSIGNED_TO | RDOF WALKOUT QC_COMPANY | RDOF WALKOUT QC_TIME_IN_HOURS | RDOF WALKOUT QC_COMPLETED_DATE | RDOF WALKOUT QC_FOOTAGE | RDOF WALKOUT QC_POINTS | REPORTS_ASSIGNED_TO | REPORTS_COMPANY | REPORTS_TIME_IN_HOURS | REPORTS_COMPLETED_DATE | REPORTS_FOOTAGE | REPORTS_POINTS | ROUTE_ASSIGNED_TO | ROUTE_COMPANY | ROUTE_TIME_IN_HOURS | ROUTE_COMPLETED_DATE | ROUTE_FOOTAGE | ROUTE_POINTS | SUBMISSION_ASSIGNED_TO | SUBMISSION_COMPANY | SUBMISSION_TIME_IN_HOURS | SUBMISSION_COMPLETED_DATE | SUBMISSION_FOOTAGE | SUBMISSION_POINTS | SUBMITTAL DOCUMENTS_ASSIGNED_TO | SUBMITTAL DOCUMENTS_COMPANY | SUBMITTAL DOCUMENTS_TIME_IN_HOURS | SUBMITTAL DOCUMENTS_COMPLETED_DATE | SUBMITTAL DOCUMENTS_FOOTAGE | SUBMITTAL DOCUMENTS_POINTS | SURVEY_ASSIGNED_TO | SURVEY_COMPANY | SURVEY_TIME_IN_HOURS | SURVEY_COMPLETED_DATE | SURVEY_FOOTAGE | SURVEY_POINTS | UTILITIES REQUEST_ASSIGNED_TO | UTILITIES REQUEST_COMPANY | UTILITIES REQUEST_TIME_IN_HOURS | UTILITIES REQUEST_COMPLETED_DATE | UTILITIES REQUEST_FOOTAGE | UTILITIES REQUEST_POINTS | WALKOUT_ASSIGNED_TO | WALKOUT_COMPANY | WALKOUT_TIME_IN_HOURS | WALKOUT_COMPLETED_DATE | WALKOUT_FOOTAGE | WALKOUT_POINTS | WALKOUT QC_ASSIGNED_TO | WALKOUT QC_COMPANY | WALKOUT QC_TIME_IN_HOURS | WALKOUT QC_COMPLETED_DATE | WALKOUT QC_FOOTAGE | WALKOUT QC_POINTS | ICON
4324bb40-58ad-4b4a-ba3f-340bd8d8TEST1 | RDOF SVC_TN_ NEW ERA RD_E1031E | TEST01 | 4249136 | DESIGN | 0 | 6/21/25 | 6/21/25 | Greenville-Tennessee | Mid-South | RESIDENTIAL LINE EXTENSION - SDU | MAGELLAN | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | ROUTE | ASSIGNED | FIBER - DESIGN - FTTH/FTTU | LOW |  | RAPID BUILD | [6 empty] | MARYVILLE-TN | E1031E |  | 1208 NEW ERA RD |  | SEVIERVILLE | TN | 37862 | 6/11/2025 12:00:00 AM | NOT FLAGGED | ATHENA GERARDO - ; ATHENA GERARDO - Bulk upload project | 1 | 2 | N/A |  | 78.72 | 6/12/2025 9:32:57 AM | N/A | NO | N/A | NO | NA | NA | NA |  | 6/11/2025 4:54:22 PM |  |  | 0 |  |  |  |  | NA |  | 0 | 0 |  |  |  | GOVERNMENT PROGRAM | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 61.61 | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 0 | [50 empty] | 0 |  |  | 17.28 | [36 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 17.11 | [36 empty] | UNREAD
4324bb40-58ad-4b4a-ba3f-340bd8d8TEST2 | RDOF SVC_TN_ NEW ERA RD_E1031E | TEST02 | 4249137 | DESIGN | 1 | 6/21/25 | 6/21/25 | Greenville-Tennessee | Mid-South | RESIDENTIAL LINE EXTENSION - SDU | MAGELLAN | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | ROUTE | ASSIGNED | FIBER - DESIGN - FTTH/FTTU | LOW |  | RAPID BUILD | [6 empty] | MARYVILLE-TN | E1031E |  | 1209 NEW ERA RD |  | SEVIERVILLE | TN | 37863 | 6/11/2025 12:00:00 AM | NOT FLAGGED | ATHENA GERARDO - ; ATHENA GERARDO - Bulk upload project | 1 | 2 | N/A |  | 79.72 | 6/12/2025 9:32:57 AM | N/A | NO | N/A | NO | NA | NA | NA |  | 6/11/2025 4:54:22 PM |  |  | 1 |  |  |  |  | NA |  | 0 | 0 |  |  |  | GOVERNMENT PROGRAM | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 61.61 | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 0 | [50 empty] | 0 |  |  | 17.28 | [36 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 17.11 | [36 empty] | UNREAD
4324bb40-58ad-4b4a-ba3f-340bd8d8TEST3 | RDOF SVC_TN_ NEW ERA RD_E1031E | TEST03 | 4249138 | DESIGN | 2 | 6/21/25 | 6/21/25 | Greenville-Tennessee | Mid-South | RESIDENTIAL LINE EXTENSION - SDU | MAGELLAN | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | ROUTE | ASSIGNED | FIBER - DESIGN - FTTH/FTTU | LOW |  | RAPID BUILD | [6 empty] | MARYVILLE-TN | E1031E |  | 1210 NEW ERA RD |  | SEVIERVILLE | TN | 37864 | 6/11/2025 12:00:00 AM | NOT FLAGGED | ATHENA GERARDO - ; ATHENA GERARDO - Bulk upload project | 1 | 2 | N/A |  | 80.72 | 6/12/2025 9:32:57 AM | N/A | NO | N/A | NO | NA | NA | NA |  | 6/11/2025 4:54:22 PM |  |  | 2 |  |  |  |  | NA |  | 0 | 0 |  |  |  | GOVERNMENT PROGRAM | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 61.61 | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 0 | [50 empty] | 0 |  |  | 17.28 | [36 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 17.11 | [36 empty] | UNREAD
4324bb40-58ad-4b4a-ba3f-340bd8d8TEST4 | RDOF SVC_TN_ NEW ERA RD_E1031E | TEST04 | 4249139 | DESIGN | 3 | 6/21/25 | 6/21/25 | Greenville-Tennessee | Mid-South | RESIDENTIAL LINE EXTENSION - SDU | MAGELLAN | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | ROUTE | ASSIGNED | FIBER - DESIGN - FTTH/FTTU | LOW | [8 empty] | MARYVILLE-TN | E1031E |  | 1211 NEW ERA RD |  | SEVIERVILLE | TN | 37865 | 6/11/2025 12:00:00 AM | NOT FLAGGED | ATHENA GERARDO - ; ATHENA GERARDO - Bulk upload project | 1 | 2 | N/A |  | 81.72 | 6/12/2025 9:32:57 AM | N/A | NO | N/A | NO | NA | NA | NA |  | 6/11/2025 4:54:22 PM |  |  | 3 |  |  |  |  | NA |  | 0 | 0 |  |  |  | GOVERNMENT PROGRAM | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 61.61 | [24 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 0 | [50 empty] | 0 |  |  | 17.28 | [36 empty] | MARTIN PRADA | SUB-CONTRACTOR: TRUENET | 0 |  |  | 17.11 | [36 empty] | UNREAD